## savar data
Project ID | Code Part 1 | Code Part 2 | Project Title | Project Name | SCHEMENAME_ENG | SCHEMENAME_BEN | PACKAGEID | Package No. | Schema_Type_id | Schema_Type_name | Upazila ID | Road ID | Length of Road (M) | DISTRICTID | Date of Completion | Name of Contractor | Date of Contract | FINANCIALYEAR | SCHEMECODE | Physical Progress (%) | STATUS | Date of Commencement | Remarks | Financial Progress (%) | Lat-long
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Bhadail Chowrastha-Pobnerteck via Bhadail Govt. Primary School road Ch. 500-1500m under Savar Upazila, District-Dhaka. (Estimate No. 21/11-12), |  |  | GDP-II/Dha/Sav/W(R)-04 | 1 | road | 36105 | 326724059 | 1160 | 361 | 2013-08-28 | M/s Johura Consturction | 2013-05-29 | 2018-19 | GDP-II/Dha/Sav/W(R)-04 | 100 | 1 | 2013-05-29 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Rajfulbaria Bus Stand-Rishipara via Fulbaria Bazar Road Ch. 00m- 650 m under Saver Upazila Dist: Dhaka. |  |  | GDP-II/Dha/sav/W(R)-11 | 1 | road | 36105 | 3267623005 | 650 | 361 | 2012-06-30 | M/S Emran Builders | 2012-03-01 | 2018-19 | GDP-II/Dha/sav/W(R)-11 | 100 | 1 | 2012-03-01 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | A) Improvement of road from Gerua Bazar to Physics Department via Moulana Bhasani Hall & Bangabandhu Sheikh Mujibur Rahman Hall of Jahangir Nagar University Ch. 00-1020m (ID No. 326724003) & B) Improvement of Baroipara (Pacca road)-Olosara road Ch. 00-65m under Savar Upazila, District-Dhaka. (Estimate No. 71/11-12) |  |  | GDP-II/DHA/Sav/W(R)-15 | 1 | road | 36105 | 326724342 | 1085 | 361 | 2012-12-25 | M/s M.S A Consturction & Engineering | 2012-06-26 | 2018-19 | GDP-II/DHA/Sav/W(R)-15 | 100 | 1 | 2012-06-26 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Gorat-Sarkar market road to Banglabazar road Ch. 00-650m under Savar Upazila, District-Dhaka. (Estimate No. 96/11-12), |  |  | GDP-II/DHA/Sav/W(R)-23 | 1 | road | 36105 | 326724246 | 650 | 361 | 2016-08-26 | M/S Howlader Enterprise & Supply | 2016-05-25 | 2018-19 | GDP-II/DHA/Sav/W(R)-23 | 100 | 1 | 2016-05-25 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Zadurchar-Hemayetpur road Ch. 00-900m under Savar Upazila, District-Dhaka. . |  |  | GDP-II/DHA/Sav/W(R)-35 | 1 | road | 36105 | 326724009 | 900 | 361 | 2014-04-14 | M/S Sumon Enterprise | 2013-12-08 | 2018-19 | GDP-II/DHA/Sav/W(R)-35 | 100 | 1 | 2013-12-08 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Jawchar Roshid Bhua Factory-Jawchar Bazar road Ch. 00-1045 Under Savar Upazila, District:Dhaka. |  |  | GDP-II/Dha/Sav/W(R)-42 | 1 | road | 36105 | 326724024 | 1045 | 361 | 2015-06-04 | M/S. Sumon Enterprise | 2014-09-29 | 2018-19 | GDP-II/Dha/Sav/W(R)-42 | 100 | 1 | 2014-09-29 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Dhaka Aricha RHD-Nimertack road Ch. 00-790 Under Savar Upazila, District:Dhaka. |  |  | GDP-II/Dha/Sav/W(R)-43 | 1 | road | 36105 | 326724306 | 790 | 361 | 2016-06-03 | M/S. Jamjam Ripa Enterprise | 2014-09-25 | 2018-19 | GDP-II/Dha/Sav/W(R)-43 | 100 | 1 | 2014-09-25 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of road from Hemayeatpur Oporupa Textile Mill-Bagbare Toslim House-Bitul Jannat Jame Mosque at Ch.253-468m. Upazila:Savar, Dist:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-49 | 1 | road | 36105 | 326725267 | 215 | 361 | 2015-06-10 | M/S. Kofil Enterprise | 2014-11-30 |  | GDP-II/DHA/Sav/W(R)-49 | 100 | 1 | 2014-11-30 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Bagbari (Agentpara) Akash-Academy-Momtaz House road Ch.00-230m. Upazila:Savar, Dist:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-67 | 1 | road | 36105 | 326725363 | 230 | 361 | 2015-10-05 | M/S. Mohsin Bul. & Const | 2015-06-14 | 2018-19 | GDP-II/DHA/Sav/W(R)-67 | 100 | 1 | 2015-06-14 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Gorapir Mazar-Dendabor Noringa Teck road (Jafor Bepari High School-Bashbari Pucca Road via Madrasha) at Ch.00-500m. Upazila:Savar, Dist:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-108 | 1 | road | 36105 | 326724381 | 500 | 361 | 2016-07-13 | Jewel Enterprise | 2016-05-11 | 2018-19 | GDP-II/DHA/Sav/W(R)-108 | 100 | 1 | 2016-05-11 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Fulbaria Bus Stand-Tetuljhora UP-Singair RHD Road Vorari Dart Garments Nagorchar Road at Ch.00-225m. Upazila:Savar, Dist:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-106 | 1 | road | 36105 | 326725373 | 225 | 361 | 2016-07-13 | M/S Jinat Enterprise | 2016-05-11 | 2018-19 | GDP-II/DHA/Sav/W(R)-106 | 100 | 1 | 2016-05-11 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Road Jadurchar-Hemayatpur Bazar Road at Ch: 950-1178m . |  |  | GDP-II/DHA/Sav/W(R)-109 | 1 | road | 36105 | 326724009 | 228 | 361 | 2016-07-14 | M/S Sumon Enterprise | 2016-05-12 | 2018-19 | GDP-II/DHA/Sav/W(R)-109 | 100 | 1 | 2016-05-12 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Road from Mushurikhola-Chaglakandi via Firingikanda road at ch. 00-1000m road |  |  | GDP-II/DHA/Sav/W(R)-97 | 1 | road | 36105 | 326724019 | 1000 | 361 | 2016-12-01 | M/S Sumon Enterprise | 2016-06-02 | 2018-19 | GDP-II/DHA/Sav/W(R)-97 | 100 | 1 | 2016-06-02 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Graveyard road Gakulnagar (Pathalia UP) vill Road at Ch: 00-170m under Upazila:Savar, Dist: Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-87 | 1 | road | 36105 | 326725370 | 170 | 361 | 26/05/16 | M/S Alamgir Hossein Co. | 26.04.16 | 2018-19 | GDP-II/DHA/Sav/W(R)-87 | 100 | 1 | 26/04/16 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Bangabondhu Road (upto Samia Gaments) (Parantik Bazar (BLRI) Ashulia UP Road at Ch: 4748-5248m under Upazila:Savar, Dist: Dhaka.(Salvage value= Tk.2,46,154.00) |  |  | GDP-II/DHA/Sav/W(R)-85 | 1 | road | 36105 | 326723017 | 500 | 361 | 2016-06-10 | M/S M.S>A Const:& Engineering | 2016-05-10 | 2018-19 | GDP-II/DHA/Sav/W(R)-85 | 100 | 1 | 2016-05-10 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Dhaka-Aricha RHD at Nirlbili Housing-Enaetpur Road (west side of Jatio Sriti Showdho) at Ch: 450-915m under Upazila:Savar, Dist: Dhaka |  |  | GDP-II/DHA/Sav/W(R)-88 | 1 | road | 36105 | 326724343 | 465 | 361 | 2016-02-06 | M/S Jewel Enterprise | 13.04.16 | 2016-17 | GDP-II/DHA/Sav/W(R)-88 | 100 | 1 | 13/04/16 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Dhanaid Yousuf Market-Tajpur Road at Ch: 00-500m under Upazila:Savar, Dist:Dhaka. . |  |  | GDP-II/DHA/Sav/W(R)-84 | 1 | road | 36105 | 326724173 | 500 | 361 | 2016-08-30 | Grenyeard construction Ltd | 2016-06-01 | 2016-17 | GDP-II/DHA/Sav/W(R)-84 | 100 | 1 | 2016-06-01 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Hazi Entas Ali pond-Mazharul House via Munshipara Road at Ch: 00-565m ) Under Upazila: Savar, District: Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-96 | 1 | road | 36105 | 326724304 | 565 | 361 | 2016-08-04 | M/S Somon Enterprise | 2016-06-02 | 2016-17 | GDP-II/DHA/Sav/W(R)-96 | 100 | 1 | 2016-06-02 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Remaining work of Zirani-Shimulia-Analbari-Nallapola Road at Ch: 00-690m Under Upazila: Savar, District:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-05 | 1 | road | 36105 | 326724080 | 690 | 361 | 2016-07-11 | M/S Jewel Engineers | 2016-05-11 | 2016-17 | GDP-II/DHA/Sav/W(R)-05 | 100 | 1 | 2016-05-11 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Road from Charabag Akran Road-H-C Bachu Miah Having (Charabag Akran Rd H/O Bachu-Miah at Kumkumary Road) at Ch: 00-500m Under Upazila: Savar, District:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-95 | 1 | road | 36105 | 326725064 | 500 | 361 | 2016-09-23 | Grenyeard construction Ltd | 2016-06-22 | 2016-17 | GDP-II/DHA/Sav/W(R)-95 | 100 | 1 | 2016-06-22 |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Road from Vakurta Mouja & Uttara Asker Hazi & Dakkink Akkel Hajir bari Road at Ch: 00-200m Under Upazila: Savar, District:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-99 | 1 | road | 36105 | 326725380 | 200 | 361 | 2016-08-11 | M/S Alamgir Hossein Co. | 2016-07-10 | 2016-17 | GDP-II/DHA/Sav/W(R)-99 | 100 | 1 | 2016-07-10 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Sadhapur puranbari Kodom Ali Market- somity Road- Harirbag road. (ch. 00-1160m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-11 | 1 | road | 36105 | 326725036 | 1160 | 361 | 2019-01-02 | M/S. Jaman Enterprise | 2018-10-28 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-11 | 100 | 1 | 2018-11-03 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Khagan- Paragram road (ch. 00-1061m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-09 | 1 | road | 36105 | 326724195 | 1061 | 361 | 2019-01-20 | M/S Sony Enterprise | 2018-11-14 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-09 | 100 | 1 | 2018-11-20 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Polli Jononi- Abdul Mannan College road (ch. 00-882) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-15 | 1 | road | 36105 | 326724103 | 882 | 361 | 2019-01-19 | M/S Labib Enterprise | 2018-11-14 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-15 | 100 | 1 | 2018-11-20 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Nabi Textile (Nabinagar-Kaliakoir RHD Rd) - Koltasuti- Barol Koborstan road) (ch. 00-565) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-13 | 1 | road | 36105 | 326724259 | 565 | 361 | 2019-01-16 | RM Construction | 2018-11-11 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-13 | 100 | 1 | 2018-11-17 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Khagan- Paragram road (ch. 1400-2827m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-55 | 1 | road | 36105 | 326724195 | 1427 | 361 | 2018-12-30 | M/S Fast Build | 2018-11-12 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-55 | 100 | 1 | 2018-11-18 |  | 100
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Jadurchar Play field. |  |  | GSIDP/DHK/DW/13 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | 2018-08-16 | M/S Sumon Enterprise | 2018-05-29 | 2018-19 | GSIDP/DHK/DW/13 | 100 | 1 |  |  | 100
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Ambagan Bazar-Kathalbagan Mosque Road at Ch: 00-500m with 2.3mx2.6m R.C.C box Culvert under Upazila:Savar, Dist: Dhaka.(Salvage value= Tk.2,23,146.00) |  |  | GDP-II/DHA/Sav/W(R)-86 | 1 | road | 36105 | 326725379 | 500 | 361 | 2016-12-24 | Global Ventures | 2016-06-23 | 2016-17 | GDP-II/DHA/Sav/W(R)-86 | 100 | 1 | 2016-06-23 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Dhaka-Aricha RHD at Upazila H/Q Shadhapur-Bongaon UP RD (Dhaka-Aricha RHD at Genda-Shadhapur Bongaon Road) at Ch: 6125-6820m under Upazila:Savar, Dist: Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-89 | 1 | road | 36105 | 326723001 | 695 | 361 | 2016-12-24 | M/S. Rubel Enterprise | 2016-06-23 | 2018-19 | GDP-II/DHA/Sav/W(R)-89 | 100 | 1 | 2016-06-23 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Nobi Textail to Barol Graveyard via Priminister Hospital (Sharbertek-Nabi Textile) Road at Ch: 1550-1892 & 00-158m under Upazila:Savar, Dist:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-83 | 1 | road | 36105 | 326725086 | 500 | 361 | 2016-08-28 | Imperial Const.& Development Ltd | 2016-05-29 | 2016-17 | GDP-II/DHA/Sav/W(R)-83 | 100 | 1 | 2016-05-29 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Remaining work for Improvement of Aragaon Primary School-Dosaid School Road at ch. 1400-2535m. Under: Savar, District: Dhaka-14. |  |  | . GDP-II/Dha/Sav/W(R)-13 | 1 | road | 36105 | 326724037 | 1135 | 361 | 2017-06-03 | M/S. Salim Enterprise | 2016-12-04 | 2016-17 | . GDP-II/Dha/Sav/W(R)-13 | 100 | 1 | 2016-12-04 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Bhatiakandi-Noihati via Nalla Polla by BC Road at CH. 000-920m. under Upazila: Savar, District: Dhaka. |  |  | . GDP-II/Dha/Sav/W(R)-133 | 1 | road | 36105 | 326724110 | 920 | 361 | 2017-06-05 | M/S. Jeuiel Enterprise | 2016-12-04 | 2016-17 | . GDP-II/Dha/Sav/W(R)-133 | 100 | 1 | 2016-12-04 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Mushurikhola- Chaglakanda via Firingikanda road by HBB under Vakurta UP Upazila Savar Dist Dhaka.Ch. 1000-1800m Road |  |  | GDP-II/DHA/Sav/WR-141 | 1 | road | 36105 | 326724019 | 800 | 361 | 2019-11-01 | Nawar Trade | 19/7/18 | 2016-17 | GDP-II/DHA/Sav/WR-141 | 100 | 1 | 19/7/18 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Condtruction of 51.06 m. Long RCC Girder Bridge on Analbari-Naihati via Nalla Pollah Road At ch. 3+250 Km. under Upazila : Savar, Dist: Dhaka. . |  |  | GDP-II/DHA/Sav/W(B)-123 | 2 | Bridge | 36105 | 326724080 | 51.06 | 361 | 2017-05-21 | Kingdom Builders Ltd | 2016-05-22 | 2016-17 | GDP-II/DHA/Sav/W(B)-123 | 100 | 1 | 2016-05-22 |  | 1
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Condtruction of 33.00 m. Long RCC Slab Bridge on Jahangirnagar Bhashani Hall-Dkkhin Shinduria. Road At ch. 2+030 Km. under Upazila : Savar, Dist: Dhaka. . |  |  | GDP-II/DHA/Sav/W(B)-124 | 2 | Bridge | 36105 | 326724003 | 33 | 361 | 2018-07-15 | M/S Rashaduzzaman Peter | 2017-07-16 | 2016-17 | GDP-II/DHA/Sav/W(B)-124 | 100 | 1 | 2017-07-16 |  | 1
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Ghandraria Pucca road - Ghandraria Deep Tubewell via Ghandraria GPS road (ch. 00-500m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-12 | 1 | road | 36105 | 326725298 | 500 | 361 | 2019-01-17 | M/S Sreejoni Construction | 2018-11-12 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-12 | 100 | 1 | 2018-11-18 |  | 1
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Nama bazar Shosan. |  |  | GSIDP/DHK/DW/16 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On Going | M/S Saba Enterprise | 2018-05-30 | 2018-19 | GSIDP/DHK/DW/16 | 90 | 0 | 2018-06-05 |  | 0
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Gazibari Purborapa |  |  | W1.00667 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-04-29 | M/S A.R Enterprise | 2018-04-25 | 2017-18 | W1.00667 | 90 | 0 | 2018-03-04 |  | 90
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Khagan |  |  | W1.00544 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-04-29 | M/S Jaman Enterprise | 2018-04-22 | 2017-18 | W1.00544 | 90 | 0 | 2018-04-30 |  | 90
408 |  |  | Need Based Infrastructure Development of Government Primary School (Project 1st Phase) | NBIDGPS-1 | Panpara |  |  | W1.00918 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-02-19 | M/S Jaman Enterprise | 2018-05-14 | 2017-18 | W1.00918 | 88 | 0 | 2018-05-20 |  | 87
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Salepur |  |  | W1.00663 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-05-19 | M/S Ela Construction | 2018-05-14 | 2017-18 | W1.00663 | 85 | 0 | 2018-05-20 |  | 60
408 |  |  | Need Based Infrastructure Development of Government Primary School (Project 1st Phase) | NBIDGPS-1 | Dhanan Joypur |  |  | W1.00770 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-04-29 | M/S Maz Business Syndicate | 2018-04-24 | 2017-18 | W1.00770 | 85 | 0 | 2018-04-30 |  | 83
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Kaundia Shosan. |  |  | GSIDP/DHK/DW/17 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On going | M/S Saba Enterprise | 2018-05-30 | 2018-19 | GSIDP/DHK/DW/17 | 80 | 0 | 2018-04-30 |  | 0
408 |  |  | Need Based Infrastructure Development of Government Primary School (Project 1st Phase) | NBIDGPS-1 | Savar Manik Chandra |  |  | W1.00772 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-01-29 | M/S A.R Enterprise | 2018-04-25 | 2017-18 | W1.00772 | 80 | 0 | 2018-04-30 |  | 72
128 |  |  | Second Rural Transport Infrastructure Project | RTIP-II | Reconstruction & maintanance Zirani Bazar- Shimulia Bazar Road Ch.00-8250m |  |  | DHA/ RPM/199 | 1 | road | 36105 | 326722002 | 8250 | 361 | 2019-03-22 | Al Amin Kindom JVA | 2016-08-01 | 2016-17 | DHA/ RPM/199 | 80 | 0 | 2016-08-07
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Kaliakoir RHD to Kumran (Chakulia) Via Komlapur Road (ch. 1803- 2101-3068m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/17-18/W-52 | 1 | road | 36105 | 326724093 | 967 | 361 | 2018-04-18 | M/S Miron Enterprise | 2018-02-19 | 2017-18 | e-tender/LGED/Dha/GOBM/17-18/W-52 | 80 | 0 | 2018-02-19 |  | 6
408 |  |  | Need Based Infrastructure Development of Government Primary School (Project 1st Phase) | NBIDGPS-1 | Kaundia |  |  | W1.00771 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-01-29 | M/S Maz Business Syndicate | 2018-04-24 | 2017-18 | W1.00771 | 72 | 0 | 2018-04-30 |  | 70
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Baitul Najat talbag Koborshan jame mosque. |  |  | GSIDP/DHK/DW/15 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On going | M/S Saba Enterprise | 2018-05-30 | 2018-19 | GSIDP/DHK/DW/15 | 70 | 0 | 2018-06-05 |  | 0
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Zirani-Shimulia Analbari-Nallapolla road Ch. 00-690m under Savar Upazila, District-Dhaka. (Estimate No. 22/11-12), , |  |  | GDP-II/Dha/Sav/W(R)-05 | 1 | road | 36105 | 32672114 | 690 | 361 | 2012-04-21 | M/S Aunika International | 2012-01-22 | 2018-19 | GDP-II/Dha/Sav/W(R)-05 | 70 | 0 | 2012-01-22 | Cancel | 70
409 |  |  | TULO | TULO | Construction of (a) Fulbaria (b) Bagdunia Union Land Office (with Boundary wall) |  |  | TULO/DHK/W-01 | 10 | Land Office | 36105 | 0 | 0 | 361 | 2019-01-08 | M/S MS Traders | 2018-03-04 | 2018-19 | TULO/DHK/W-01 | 70 | 0 | 2018-03-11
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Dhaka Aricha Highway - Ashulia GC road. (ch. 3140-3185m & 6520-7100m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-37 | 1 | road | 36105 | 326722001 | 625 | 361 | 2019-02-12 | M/S Labib Enterprise | 2018-11-22 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-37 | 50 | 0 | 2018-11-28 |  | 0
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Dhaka Aricha RHD 20 mile- Zirabo bazar road( Dewan Ideris road) road. (ch. 2325-2375m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-14 | 1 | road | 36105 | 326723003 | 0.05 | 361 | 2018-12-18 | Geneva International | 2018-11-13 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-14 | 30 | 0 | 2018-11-19 |  | 0
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Dhaka Aricha RHD Senwalia - Dhaka Co Oparative Society Kurgaon road. (ch. 00-1196m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-10 | 1 | road | 36105 | 326724228 | 1196 | 361 | 2019-01-18 | Geneva International | 2018-11-13 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-10 | 10 | 0 | 2018-11-19 |  | 0
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Aragaon Primary School-Doshaid School road Ch. 1400-2535m under Savar Upazila, District-Dhaka. (Estimate No. 53/11-12) |  |  | GDP-II/DHA/Sav/W(R)-13 | 1 | road | 36105 | 326724037 | 1135 | 361 | 2012-08-02 | M/S Future Castle Constriction | 2012-04-03 | 2018-19 | GDP-II/DHA/Sav/W(R)-13 | 10 | 0 | 2012-04-03 |  | 100
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Shampur Bazar to Horindora Tanarir More road (ch. 00-475m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/18-19/W-56 | 1 | road | 36105 | 326724345 | 475 | 361 | 2019-08-26 | M/S Sowadh Enterprise | 2019-02-19 | 2018-19 | e-tender/LGED/Dha/GOBM/18-19/W-56 | 0 | 0 | 2019-02-25 |  | 0
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Sree Sree Ramkrisna & Pochoboti Ashom. |  |  | GSIDP/DHK/DW/14 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On going | M/S Saba Enterprise | 2018-05-30 | 2018-19 | GSIDP/DHK/DW/14 | 0 | 0 | 2018-06-05 |  | 0
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Firingikanda Kobosthan. |  |  | GSIDP/DHK/DW/11 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On going | M/S ruma Enterprise | 2018-05-29 | 2018-19 | GSIDP/DHK/DW/11 | 0 | 0 | 2018-06-05 |  | 0
345 |  |  | General Social Infrastructure Development Project | GSIDP | Improvement of Amin Bazar Central Koborsthan. |  |  | GSIDP/DHK/DW/12 | 10 | Mosque/ Mondir | 36105 | 0 | 0 | 361 | On going | M/S ruma Enterprise | 2018-05-29 | 2018-19 | GSIDP/DHK/DW/12 | 0 | 0 | 2018-06-04 |  | 0
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Minnot Ali RPS |  |  | W1.02122 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-09-30 | M/S Nirman Prokausholy | 2018-12-19 | 2018-19 | W1.02122 | 0 | 0 | 2018-12-30 |  | 0
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Nikrail Com RPS |  |  | W1.02123 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-09-30 | Trade Box International | 2018-12-19 | 2018-19 | W1.02123 | 0 | 0 | 2018-12-30 |  | 0
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Toyubpur RPS |  |  | W1.02124 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-09-30 | M/S Johura Enterprise | 2018-12-19 | 2018-19 | W1.02124 | 0 | 0 | 2018-12-30 |  | 0
407 |  |  | Need Based Infrastructure Development of Newly Nationalized Government Primary School (1st Phase) | (NBIDNNGPS-1) | Uttara RPS |  |  | W1.02121 | 3 | School Building | 36105 | 0 | 0 | 361 | 2019-09-30 | M/S Sumon Enterprise | 2018-12-24 | 2018-19 | W1.02121 | 0 | 0 | 2018-12-30 |  | 0
220 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-II | Improvement of Road from Solai Market-Uttar Baherchar Road at Ch: 00-615m Under Upazila: Savar, District:Dhaka. |  |  | GDP-II/DHA/Sav/W(R)-98 | 1 | road | 36105 | 32724320 | 615 | 361 | 2016-07-26 | M/S Abdul Based Jihadi | 2016-05-25 |  | GDP-II/DHA/Sav/W(R)-98 | 0 | 0 | 2016-05-25 |  | 0
403 |  |  | Rural Road & Culvert maintenance Program (GOBM) | GOBM | Maintenance of Norsihpur Bazar - Toyobpur road via Nischintopur Primary School Road ( ch. 00-2009m) Under Savar, Dist- Dhaka. |  |  | e-tender/LGED/Dha/GOBM/17-18/W-81 | 1 | road | 36105 | 326724384 | 2009 | 361 | 2018-07-24 | M/S Sayed & Brothers | 2018-05-13 | 2017-18 | e-tender/LGED/Dha/GOBM/17-18/W-81 | 0 | 0 | 2018-05-13 |  | 0
405 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-III | a Improvement of Kaisharchar-Nonder Khamar Kheaghat Road Kaisharchar pucca road via Domrakanda madrasha Nonder Khamar Ch. 00 to 1000m under Upazila Savar District Dhaka. Road ID no 326724270. Total salvage amount Tk. 348995.00 b Improvement of Chunarchar Main chunarchar Madrasa-Itakhola Road- Bottoli Road Ch. 00646m under Upazila Savar District Dhaka. |  |  | GDP-3/D-30 | 1 | Road | 36105 | 326724371 | 1164 | 361 | 2020-02-05 | M/S. Sumon Enterprise | 2020-02-05 | 2018-19 | GDP-3/D-30 | 0 | 0 | 2019-02-06 |  | 0
405 |  |  | Rural Infrastructure Development Project: Greater Dhaka Tangail & Kishorganj Zila | GDP-III | (a) Maintenance of Varalipara Shamlashi - Baherpur Baherchar Road at Ch.0000m-1844km under Upazila Savar District Dhaka. Road ID no. 326724035 (b) Maintenance of Hemaetpur Bus stand Joynabari varai Road at Ch. 1650-2650m. under Upazila Savar District Dhaka. Road ID no. 326724101 (c) Maintenance of Chan Mia Member house - Firing Renge via Usha Poultry Farm Road at Ch. 00-670m. under Upazila Savar District Dhaka. |  |  | GDP-3/D-32 | 1 | Road | 36105 | 326724243 | 3510 | 361 | 2020-02-04 | Fast Buld | 2019-02-05 | 2018-19 | GDP-3/D-32 | 0 | 0 | 2019-02-05 |  | 0
54 |  |  | LBC | LBC | Construction of Remaining Works of 66.00 m RCC Bridge on Bolivodro GC-Dhamsona UP Shimulia UP Road at Ch. 4465.00 under Upazila Savar District Dhaka |  |  | Package No. PD/CLBUURP/W-136B | 2 | Bridge | 36105 | 0 | 66 | 361 | On Going | M/S Sayed & Brothers | 2018-05-30 | 2018-19 | Package No. PD/CLBUURP/W-136B | 0 | 0 | 2018-05-30 |  | 0

## Shivalaya data
Project ID | Code Part 1 | Code Part 2 | Project Title | Project Name | SCHEMENAME_ENG | SCHEMENAME_BEN | PACKAGEID | Package No. | Schema_Type_id | Schema_Type_name | Upazila ID | Road ID | Length of Road (M) | DISTRICTID | Date of Completion | Name of Contractor | Date of Contract | FINANCIALYEAR | SCHEMECODE | Physical Progress (%) | STATUS | Date of Commencement | Remarks | Financial Progress (%) | Lat-long
223 |  |  | EUCP, Extension of Upazila Complex Project (EUCP) | EUCP | Construction of Extended Administrative Bhavan & Hall Room under Shibalaya Upazila,District: Manikganj. |  |  | PWA-UZC-Shibalay-103 | 4 | Administrative building | 36606 | 0 | 0 | 366 | 2017-08-21 | Starlite Services Limited | 2015-07-26 | 2015-16 | PWA-UZC-Shibalay-103 | 100 | 1 | 2015-09-15 |  | 96.75
261 |  |  | IRIDP | IRIDP-II | Improvement of Machain Bazar Est Mosque-Mr.Zia house road ( Ch.0.00m-800m) under Shibalaya Upazila,Manikganj. |  |  | IRIDP/MNK/DW-88 | 1 | road | 36606 | 356785056 | 800 | 366 | 2015-06-30 | M/S. Rupali Construction | 2015-04-29 | 2014-15 | IRIDP/MNK/DW-88 | 100 | 1 | 2015-05-26 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Choto Anulia-Nobogram R&H via Kasadha Switch gate & Nobograme Saheb Ali house Road at Ch. 0.0m - 1200.0m. (ID No. 39904). |  |  | IRIDP-2/MNK/DW-39 | 1 | road | 36606 | 356784002 | 1200 | 366 | 2016-12-09 | M/S.Al-Mamun Traders | 2016-02-09 | 2015-16 | IRIDP-2/MNK/DW-39 | 100 | 1 | 2016-02-16 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of (A) Falsati Juni Kalsa More-Sakrail Bazar via Maniknagar Road at Ch. 0.0 m - 1008 m. & (B) Construction of 1 No 0.625x0.600m Culvert at Ch. 750m on the same road. |  |  | IRIDP/MNK/DW-40 | 1 | road | 36606 | 356784063 | 1008 | 366 | 2016-11-15 | M/S. Himel Traders | 2016-02-15 | 2015-16 | IRIDP/MNK/DW-40 | 100 | 1 | 2016-02-22 |  | 100
261 |  |  | IRIDP | IRIDP-II | a) Improvement of Jaforganj GC(Dhushar-Ghior GC via Nayabari Bazar Bardhamankandi,Bhorrah bz & Thakurkandi GPS road from Ch. 1480-2556m. With 2 nos Box Culvert at Ch. 1765m & 2192m |  |  | IRIDP-II/MNK/DW-37 | 1 | road | 36606 | 356784001 | 1076 | 366 | 18/02/17 | M/S.Al-Mamun Traders | 19/04/16 | 2015-16 | IRIDP-II/MNK/DW-37 | 60 | 0 | 2016-04-26 |  | 0
261 |  |  | IRIDP | IRIDP-II | Improvement of Shibrampur BRDB office-Shafiuddin house via Hakim Master house,Tepra Central Graveyard road Ch. 170-615m & link 50m |  |  | IRIDP-2/MNK/DW-38 | 1 | road | 36606 | 356785038 | 495 | 366 | 2016-11-15 | M/S. Nisa & Bappy Enterprise | 2016-02-15 | 2015-16 | IRIDP-2/MNK/DW-38 | 100 | 1 | 2016-02-22 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Boali(Shibalaya Dispensary)-Padma-Jamuna River Bank road Ch. 0.00-1647m |  |  | IRIDP-2/MNK/DW-41 | 1 | road | 36606 | 356784018 | 1647 | 366 | 2016-12-14 | M/S.Al-Mamun Traders | 2016-03-13 | 2015-16 | IRIDP-2/MNK/DW-41 | 100 | 1 | 2016-03-20 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Gandhair-Poyla via Mirpur Kolema Khatun GPS road road Ch. 0.00-650m |  |  | IRIDP-2/MNK/DW-52 | 1 | road | 36606 | 356784021 | 650 | 366 | 2017-03-28 | M/S.Reba Construction | 2016-09-27 | 2016-17 | IRIDP-2/MNK/DW-52 | 100 | 1 | 2016-10-04 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Arua UP Office-Mavhain GC via Shaljana road Ch. 0.00-1000m |  |  | IRIDP/MNK/DW-51 | 1 | road | 36606 | 356783007 | 1000 | 366 | 2017-03-28 | M/S.Raka Enterprise | 2016-09-28 | 2016-17 | IRIDP/MNK/DW-51 | 100 | 1 | 2016-10-05 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Dhaka-Aricha NHW(Folsatia)-Machain GC via Sakrail Bazar road Ch. 3115-4350m |  |  | IRIDP-II/MNK/DW-50 | 1 | road | 36606 | 356782010 | 1235 | 366 | 24/4/2017 | M/S.M.M Bricks | 16/10/16 | 2017-18 | IRIDP-II/MNK/DW-50 | 100 | 1 | 2016-10-23 |  | 70
261 |  |  | IRIDP | IRIDP-II | Improvement of (a) Amdala Bazar-Tarail Bridge via Maniknagar road drom Ch. 2960-4160m under Shibalaya Upazila,(b) Construction of 02 nos 1x2.00x2.00m Culvert at Ch: 3004m & 3334m on the same road © Construction of 01 no, 1x2.50x2.00m Culvert at Ch: 3600m on the same road. |  |  | IRIDP-2/MNK/DW-57 | 1 | road | 36606 | 356784009 | 1200 | 366 | 2017-10-03 | M/S. Reba Construction | 2017-01-03 | 2017-18 | IRIDP-2/MNK/DW-57 | 100 | 1 | 2017-01-10 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Hazirbadha Botgash-Nobogram LGED Bridge via Natun Faridpur road Ch. 1650m-2280m |  |  | IRIDP-2/MNK/DW-59 | 1 | road | 36606 | 356784019 | 630 | 366 | 2017-08-06 | M/S. Himel Traders | 2017-01-31 | 2017-18 | IRIDP-2/MNK/DW-59 | 100 | 1 | 2017-02-07 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Nilgram-Tawakhali via Kodalia Primary School road Ch. 347m-1100m |  |  | IRIDP-2/MNK/DW-60 | 1 | road | 36606 | 356784024 | 753 | 366 | 2017-08-06 | M/S. Himel Traders | 2017-01-31 | 2017-18 | IRIDP-2/MNK/DW-60 | 100 | 1 | 2017-02-07 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Ulail UP Office ( Rupsa)-Upazila H/Q( Tepra) road Ch. 00-900m |  |  | IRIDP-2/MNK/DW-58 | 1 | road | 36606 | 356783005 | 900 | 366 | 2017-08-05 | M/S. Israfil Traders | 2017-01-31 | 2017-18 | IRIDP-2/MNK/DW-58 | 100 | 1 | 2017-02-07 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Butuni Bazar-Paragram via Basepara khal road from Ch. 870-1100m |  |  | IRIDP-2/MNK/DW-111 | 1 | road | 36606 | 356784049 | 330 | 366 | 2018-05-22 | M/S. Hanif Traders | 2017-11-22 | 2018-19 | IRIDP-2/MNK/DW-111 | 100 | 1 | 2017-02-07 |  | 100
261 |  |  | IRIDP | IRIDP-II | Improvement of Kakkol-Intajgonj Bazar via Jamunabad road Ch. 00m-1500m |  |  | IRIDP/MNK/DW-87 | 1 | road | 36606 | 356784012 | 1500 | 366 | 2015-06-30 | M/S. Rupali Construction | 2015-04-29 | 2015-16 | IRIDP/MNK/DW-87 | 100 | 1 | 2015-05-08 |  | 100
261 |  |  | IRIDP | IRIDP-II | (A) Improvement of Dhaka-Aricha NHW of Khamarpara Ekhlas Pir. House- Nannu house via Mr. Mannan Chairman house road from Ch: 00-472m & ( B) Improvement of Khudra Tepra Ekhlas Pir.Saheb House which start from Mannan house-Jalal house road from Ch: 250-750m under Shibalaya, Manikganj. |  |  | IRIDP-II/MNK/DW-72 | 1 | road | 36606 | 356785039 | 972 | 366 | 2018-01-16 | M/S Twin Trade | 2017-05-17 | 2018-19 | IRIDP-II/MNK/DW-72 | 40 | 0 | 2017-05-24 |  | 0
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Constructcion of Additional room(Vertical Extension) for Maluchi GPS including furniture supply. |  |  | PEDP-III/MNK/SHI/2011-2012/W1.0551 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-12-02 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W1.0551 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Constructcion of Additional room(Vertical Extension) for Moddanagar GPS including furniture supply. |  |  | PEDP-III/MNK/SHI/2011-2012/W1.0551 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-12-02 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W1.0551 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintanance of Baradia RNGPS |  |  | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-07-01 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintanance of Butuni GPS |  |  | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-07-01 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintanance of Magurail GPS |  |  | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-07-01 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintanance of Moddhanagar GPS |  |  | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 3 | school building | 36606 | 0 | 0 | 366 | 2013-07-01 | M/S.Rana Enterprise | 2013-07-01 | 2014-15 | PEDP-III/MNK/SHI/2011-2012/W3.0333 | 100 | 1 | 2013-07-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Constructcion of Additional room for Annaypur GPS . |  |  | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 3 | school building | 36606 | 0 | 0 | 366 | 18/06/2014 | M/S. Sthapati Construction | 18/06/2014 | 2014-15 | e-Tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 100 | 1 | 2014-06-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Constructcion of Additional room for Kathalia GPS . |  |  | e-tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 3 | school building | 36606 | 0 | 0 | 366 | 2015-06-18 | M/S. Sthapati Construction | 18/06/2014 | 2014-15 | e-tender/PEDP-III/MNK/SHI/2013-14/W2.2863 | 100 | 1 | 2014-06-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintanance of Mohadebpur GPS |  |  | e-Tender/PEDP-III/MNK/SHI/2014-2015/W3.0495 | 3 | school building | 36606 | 0 | 0 | 366 | 2014-06-18 | M/S Hanif Traders | 2015-06-18 | 2014-15 | e-Tender/PEDP-III/MNK/SHI/2014-2015/W3.0495 | 100 | 1 | 2014-06-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room Poyla GPS under Shibalaya, Manikganj.(Vertical-2 room) |  |  | PEDP-III/MNK/SHI/2015-16/W2.5024 | 3 | school building | 36606 | 0 | 0 | 366 | 1917-02-10 | M/S. M.A Quddus | 2016-01-03 | 2015-16 | PEDP-III/MNK/SHI/2015-16/W2.5024 | 100 | 1 | 1917-02-10 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Falsatia Primary School Upazila-Shibalay Dist- Manikgonj.(Vertical=3 Rooms with Stair). |  |  | PEDP-III/MNK/SHI/2015-16/W2.5217 | 3 | school building | 36606 | 0 | 0 | 366 | 2016-10-05 | M/S. Nurul Islam | 2016-03-23 | 2015-16 | PEDP-III/MNK/SHI/2015-16/W2.5217 | 100 | 1 | 2016-10-05 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Purbo Shahily Primary School Upazila-Shibalay Dist- Manikgonj. (Horizontal=3 Rooms with Stair) |  |  | PEDP-III/MNK/SHI/2015-16W2.5305 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-01-05 | M/S. Nurul Islam | 23/03/16 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5305 | 100 | 1 | 2017-01-05 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Billpara Primary School Upazila-Shibalay Dist- Manikgonj. (Horizontal=3 Rooms , Vertical=2 Rooms with Stair) |  |  | PEDP-III/MNK/SHI/2015-16W2.5758 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-05-02 | M/S. M.A Quddus | 2016-04-04 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5758 | 100 | 1 | 2017-05-02 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Dorikandi Primary School Upazila-Shibalay Dist- Manikgonj. (Horizontal=2 Rooms ,with Stair) |  |  | PEDP-III/MNK/SHI/2015-16W2.5758 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-05-02 | M/S. M.A Quddus | 2016-04-04 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5758 | 100 | 1 | 2017-05-02 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Rupsa Primary School Upazila-Shibalay Dist- Manikgonj. (Horizontal=2 with Stair) |  |  | PEDP-III/MNK/SHI/2015-16W2.5759 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-01-11 | M/S. L. Rahman Traders | 23/3/16 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5759 | 100 | 1 | 2017-01-11 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenance of Shibalaya GPS under Shibalaya, Manikganj. |  |  | PEDP-III/MNK/SHI/2015-16W2.5759 | 3 | school building | 36606 | 0 | 0 | 366 | 2016-10-02 | M/S. M.A Quddus | 23/3/16 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5759 | 100 | 1 | 2016-10-02 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Doschira Primary School ( Horizontal = 2 Rooms Upazila-Shibalaya, Dist. Manikganj. |  |  | PEDP-III/MNK/SHI/2015-16W2.5941 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-04-30 | M/S. Sthapoti Construction | 2016-04-25 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5941 | 100 | 1 | 2017-04-30 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Dhushar Primary School Horizonal-3 & Vertical=1 Room with Stair) Upazila-Shibalaya, Dist. Manikganj. |  |  | PEDP-III/MNK/SHI/2015-16W2.5941 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-04-30 | M/S. Sthapoti Construction | 2016-04-25 | 2015-16 | PEDP-III/MNK/SHI/2015-16W2.5941 | 100 | 1 | 2017-04-30 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room Nali Bororia GPS under Shibalaya, Manikganj.(Horizontal-3 & Vertical-3 room with stair) |  |  | PEDP-III/MNK/SHI/2016-17/W2.6182 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-12-31 | BB-ME JV | 2016-10-25 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W2.6182 | 100 | 1 | 2016-07-02 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Tangor Hata Primary School Upazila-Shibalay Dist- Manikgonj.(Horizantal)=6 Rooms with Stair). |  |  | PEDP-III/MNK/SHI/2016-17/W2.6183 | 3 | school building | 36606 | 0 | 0 | 366 | 1917-06-12 | Hanif-Salim JV | 1916-11-01 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W2.6183 | 100 | 1 | 2016-11-08 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Tangor Hata Primary School Upazila-Shibalay Dist- Manikgonj.((Hoeizntal) =3 Rooms with Stair). |  |  | PEDP-III/MNK/SHI/2016-17/W2.6852 | 3 | school building | 36606 | 0 | 0 | 366 | 1917-06-08 | Hanif-Salim JV | 1917-01-31 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W2.6852 | 100 | 1 | 2017-01-07 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Additional Class Room of Mohadebpur Primary School Upazila-Shibalay Dist- Manikgonj |  |  | PEDP-III/MNK/SHI/2016-17/W2.6455 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-09-20 | M.A Quddus | 1917-02-13 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W2.6455 | 100 | 1 | 2017-02-20 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenance of Choto Anulia & Nihalpur Primary School Upazila-Shibalay Dist- Manikgonj |  |  | PEDP-III/MNK/SHI/2016-17/W3.1034 | 3 | school building | 36606 | 0 | 0 | 366 | 1917-04-04 | M/S. M.A Quddus | 1917-01-03 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W3.1034 | 100 | 1 | 2017-01-10 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Boundary Wall & Main Gate of Jumduara Govt. Primary School |  |  | PEDP-III/MNK/SHI/2016-17/W17.109 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-10-03 | M/S Maksud Engineeron woeks | 2017-05-28 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W17.109 | 100 | 1 | 2017-06-05 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Extension & Removation of Shibalaya Upazila Education Office |  |  | PEDP-III/MNK/SHI/2016-17/W7.359 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-10-02 | M/S.Selim Construction | 2017-06-26 | 2016-17 | PEDP-III/MNK/SHI/2016-17/W7.359 | 100 | 1 | 2017-07-02 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Maintenance of Upazila URC Building Shibalaya Upazila, District-Manikganj. |  |  | PEDP-III/MNK/SHI/2016-17/W17.0333 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-05-16 | M/S. Habib Construction | 2017-04-17 | 2017-18 | PEDP-III/MNK/SHI/2016-17/W17.0333 | 100 | 1 | 2017-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Furniture Supply of Upazila URC Office under Shibalaya, Manikganj. |  |  | PEDP-III/MNK/SHI/2016-17/G2.0323 | 3 | school building | 36606 | 0 | 0 | 366 | 2017-05-16 | M/S. Habib Construction | 2017-04-17 | 2017-18 | PEDP-III/MNK/SHI/2016-17/G2.0323 | 100 | 1 | 2017-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Boundary Wall including gate of Butuni, Choto Anulia & Das Kandi GPS |  |  | PEDP-III/MNK/SHI/2017-18/W17.603 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-07-16 | M/S. R.F JV | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W17.603 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Boundary Wall including gate of Gonga Proshad, Mohadebpur & Nihalpur-2 REG |  |  | PEDP-III/MNK/SHI/2017-18/W17.604 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-07-16 | M/S. R.F JV | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W17.604 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Construction of Boundary Wall including gate of Noyabari, Rupsa & Uthali GPS |  |  | PEDP-III/MNK/SHI/2017-18/W17.605 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-07-16 | M/S. R.F JV | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W17.605 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenanace of Amdala, Dubulia Danga & Dhubulia GPS |  |  | PEDP-III/MNK/SHI/2017-18/W3.1798 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-06-10 | M/S. Rana Enterprise | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W3.1798 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenanace of Kalagaria Community School & Ragunatha GPS |  |  | PEDP-III/MNK/SHI/2017-18/W3.1799 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-06-10 | M/S. M.A Quddus | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W3.1799 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenanace of Nali Bororia GPS |  |  | PEDP-III/MNK/SHI/2017-18/W3.2270 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-06-10 | M/S. Rana Enterprise | 2018-04-17 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W3.2270 | 100 | 1 | 2018-04-25 |  | 100
105 |  |  | Primary Education Development Project-3 | PEDP-3 | Major Maintenanace of Upazila Upzaila Education Office. |  |  | PEDP-III/MNK/SHI/2017-18/W7.508 | 3 | school building | 36606 | 0 | 0 | 366 | 2018-06-25 | M/S.Bashar Enterprise | 2018-05-20 | 2017-18 | PEDP-III/MNK/SHI/2017-18/W7.508 | 100 | 1 | 2018-05-27 |  | 100
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of Class room of Nayabari Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.00593 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-02-07 | M/S. Dewan Traders | 2018-05-08 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.00593 | 80 | 0 | 2018-05-15 |  | 70
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Daskandi Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.00707 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-02-07 | M/S. Rana Enterprise | 2018-05-08 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.00707 | 95 | 0 | 2018-05-15 |  | 80
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Tarail Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01293 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-03-04 | M/S. Villege Enterprise | 2018-06-05 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01293 | 95 | 0 | 2018-06-12 |  | 80
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Amdala Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01849 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-09-14 | M/S. Dorbesh Enterprise | 2018-10-23 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01849 | 0 | 0 | 2018-11-30 |  | 0
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Birajpur Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01850 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-09-14 | M/S. Atique Construction | 2018-10-23 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01850 | 0 | 0 | 2018-11-30 |  | 0
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Paragrame Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01851 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-09-14 | M/S. Megnah Builders | 2018-10-23 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01851 | 0 | 0 | 2018-11-30 |  | 0
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Uthali Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01852 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-09-14 | M/S. Khan Borthers Construction | 2018-10-23 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.01852 | 0 | 0 | 2018-11-30 |  | 0
408 |  |  | Need Based Infrastructure Development of Government Primary School(1st Phase) | NBIDGPS-1 | Construction of class room of Teota Govt. Primary School under NBIDGPS |  |  | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.02048 | 3 | school building | 36606 | 0 | 0 | 366 |  | M/S. Simanta Enterprise | 17/3/19 | 2017-18 | e-Tender/NBIDGPS/Man/Shi/2017-18/W1.02048 | 0 | 0 | 27/3/19 |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Dubuliadanga Govt. Primary School under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2017-18/W1.00740 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-05-07 | M/S. Mir Nirman Enterprise | 2018-05-08 | 2017-18 | e-Tender/NBIDNNGPS/Man/Shi/2017-18/W1.00740 | 90 | 0 | 2018-05-15 |  | 80
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Choto Anulia Govt. Primary School under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2017-18/W1.00750 | 3 | school building | 36606 | 0 | 0 | 366 | 2019-05-07 | M/S. Rana Enterprise | 2018-05-08 | 2017-18 | e-Tender/NBIDNNGPS/Man/Shi/2017-18/W1.00750 | 85 | 0 | 2018-05-15 |  | 70
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Bockchar GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02838 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02838 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Bardamankandi GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02839 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02839 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Ghonapara GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02840 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02840 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Dubulia GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02841 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02841 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Koyra GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02842 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02842 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Chok Dubulia GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02843 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02843 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Dakhin Shakrail GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02844 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02844 | 0 | 0 |  |  | 0
407 |  |  | Need Based Infrastucture Development of Newly Nationalized Government Primary School(1st Phase) | NBIDNNGPS-1 | Construction of Class Room Kalagaria GPS under NBIDNNGPS Project-1. |  |  | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02845 | 3 | school building | 36606 | 0 | 0 | 366 |  |  |  | 2018-19 | e-Tender/NBIDNNGPS/Man/Shi/2018-19/W1.02845 | 0 | 0 |  |  | 0
405 |  |  | Grater Dhaka Project-3 | GDP-3 | Rehabilitation of Shimulia (Afsar Chairman house more)-Boro Butuni Bazar road at Ch. 00.2500m. |  |  | GDP-3/MA-Reh-2 | 1 | road | 36606 | 356784038 | 2500 | 366 | 2018-10-15 | M/S.M.A Quddus | 2018-05-16 | 2018-19 | GDP-3/MA-Reh-2 | 100 | 1 | 2018-05-22 |  | 100
406 |  |  | UNR-GDP | UNR-GDP | Improvement of Ulail UP Office(Gandhair More)-Diarchar Sakrail Bazar Road from Ch. 0.0m - 503.0m. ( Tender ID No. 46167). |  |  | UNR-GDP-MA-113 | 1 | road | 36606 | 356783002 | 503 | 366 | 2016-05-13 | M/S. Maksud Engineering Works | 2016-05-13 | 2016-17 | UNR-GDP-MA-113 | 100 | 1 | 2016-03-21 |  | 100
406 |  |  | UNR-GDP | UNR-GDP | Improvement of Jaforgonh GC(Gabtali More)-Ghior UP Office via Nayabari,Bohulakul road from Ch. 2600.0 m - 3000 m. (Tender ID No: 46168) |  |  | UNR-GDP-MA-114 | 1 | road | 36606 | 356783008 | 400 | 366 | 2016-05-09 | M/S. Uzzal Enterprise | 2016-03-10 | 2016-17 | UNR-GDP-MA-114 | 100 | 1 | 2016-03-20 |  | 100
406 |  |  | UNR-GDP | UNR-GDP | Improvement of Amdala Bazar-Tarail Bazar Bridge via Dakhin Ulail Bazar road at Ch: 0.00m-500.00m. |  |  | e-Tender/UNR-GDP-MK-100 | 1 | road | 36606 | 356784009 | 500 | 366 | 2015-11-25 | M/S. Z. Islam | 2015-05-25 | 2015-16 | e-Tender/UNR-GDP-MK-100 | 100 | 1 | 2015-05-31 |  | 100
406 |  |  | UNR-GDP | UNR-GDP | Improvement of Dakhin Ulail Ainal Mistri-Birajpur Hasmot Master house via Birajpur GPS road at Ch: 0.00m-500.00m. |  |  | e-Tender/UNR-GDP-MK-101 | 1 | road | 36606 | 356784056 | 500 | 366 | 2015-11-25 | M/S. Z. Islam | 2015-05-25 | 2015-16 | e-Tender/UNR-GDP-MK-101 | 100 | 1 | 2015-05-31 |  | 100
406 |  |  | UNR-GDP | UNR-GDP | Improvement of Mohadebpur Kishi Bank- Vabanipur - road at Ch. 0+000 Km-0+700 Km. |  |  | UNR-GDP-MA-109 | 1 | road | 36606 | 356784044 | 700 | 366 | 2016-05-02 | M/S.Twin Trade | 2016-02-15 | 2016-17 | UNR-GDP-MA-109 | 100 | 1 | 2016-02-22 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Improvement of Jaforgonj GC-(Gabtali More)-Samganj GC via Roha road at Ch. 0.00m-1200.00m. |  |  | GDP-II/MNK/Shib/W(R)-08 | 1 | road | 36606 | 356782011 | 1200 | 366 | 17/12/2012 | M/S. Joya Enterprise | 22/04/2012 | 2012-13 | GDP-II/MNK/Shib/W(R)-08 | 100 | 1 | 2012-05-01 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Improvement of Shimulia (Razzak Member house)-Gala UP Office(Harirampur)Via Choto Butuni & Fachuadhara Bridge road at Ch. 375.00m-1350.00m. |  |  |  | 1 | road | 36606 | 0 | 975 | 366 | 17/12/2012 | M/S. Rana Enterprise | 22/04/2012 | 2012-13 |  | 100 | 1 | 29/04/19 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Construction of 30.00m ling RCC Girder bridge on Bejpara high School-Kachidhara Bot tree road at Ch: 0.00m. |  |  | GDP-II/MNK/Shib/W(B)-21 | 2 | bridge/culvert | 36606 | 356784035 | 30 | 366 | 2014-09-19 | M/S. Debesh Traders | 2013-12-24 | 2012-13 | GDP-II/MNK/Shib/W(B)-21 | 100 | 1 | 2014-01-01 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | (A) Improvement of Mohadebpur UP Office(Bus Stand) Dotara Bridge(Ghior R&H) via Purboshahely Ch: 240-700m(ID No: 356783010) (B) Construction of 3x3.70x5.00m RCC Box Culvert on Same road at Ch: 700m. |  |  | GDP-II/MNK/Shib/W(R)-37 | 1 | road | 36606 | 356783010 | 700 | 366 | 2015-01-06 | M/S.Sentu & Sons Builders | 2014-02-09 | 2014-15 | GDP-II/MNK/Shib/W(R)-37 | 100 | 1 | 2019-02-17 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Improvement of Gandhair-Shatghor(Teota Bachet) road at Ch. 60.00m-1200.00m. |  |  | GDP-II/MNK/Shib/W(R)-46 | 1 | road | 36606 | 356784033 | 600 | 366 | 2015-07-21 | M/S. Hasib Enterprise | 2015-01-22 | 2014-15 | GDP-II/MNK/Shib/W(R)-46 | 100 | 1 | 2015-02-01 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | (A) Improvement of Teota Bazar under Shibalaya, Manikgabj |  |  | GDP-II/MNK/Shib/W(BA)-51 | 5 | growth center/market | 36606 | 0 | 0 | 366 | 2015-10-20 | M/S. Hanif Traders | 2015-04-23 | 2014-15 | GDP-II/MNK/Shib/W(BA)-51 | 100 | 1 | 2015-04-30 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | (A) Improvement of Nayabari Bazar under Shibalaya, Manikgabj |  |  | GDP-II/MNK/Shib/W(BA)-50 | 5 | growth center/market | 36606 | 0 | 0 | 366 | 2015-10-20 | M/S. Shohag Construction | 2015-04-23 | 2014-15 | GDP-II/MNK/Shib/W(BA)-50 | 60 | 0 | 2015-04-30 |  | 40
220 |  |  | Grater Dhaka Project-2 | GDP-II | Boro Butuni Bazar-Kachidhara Bottala via Bejpara high School road. |  |  | GDP-II/MNK/Shib/W(R)-74 | 1 | road | 36606 | 356784012 | 869 | 366 | 2017-02-25 | M/S. Al-Mamon Traders | 26/04/16 | 2015-16 | GDP-II/MNK/Shib/W(R)-74 | 100 | 1 | 2016-03-21 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Falsatia-Machain Bazar road Kesobpoty Sudon Kumar guha house to Kesobpoty Jame Mosque road. At Ch.0.00m-360.00m |  |  | GDP-II/MNK/Shib/W(R)-72 | 1 | road | 36606 | 356784062 | 360 | 366 | 2016-11-28 | M/S.Pervas Enterprise | 2016-02-28 | 2015-16 | GDP-II/MNK/Shib/W(R)-72 | 100 | 1 | 2016-02-06 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Improvement of Shibrampur BRDB Office - Tepra Central Graveyard road via Hakim Master house road. At Ch. 0-170m & Ch.615-743m. |  |  | GDP-II/MNK/Shib/W(R)-73 | 1 | road | 36606 | 356785038 | 298 | 366 | 2016-11-16 | M/S. M A Quddus | 2016-02-16 | 2015-16 | GDP-II/MNK/Shib/W(R)-73 | 100 | 1 | 2016-02-23 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Improvement of Kakkal-Intajgonj bazar via jomunabad road.at Ch.1500-1850m |  |  |  | 1 | road | 36606 | 0 | 350 | 366 | 2016-12-14 | M/S. Al-Mamon Traders | 2016-03-14 | 2015-16 |  | 100 | 1 | 2019-03-22 |  | 100
220 |  |  | Grater Dhaka Project-2 | GDP-II | Construction of 54.00m RCC Grader Bridge on Baradia-Moynargudara at Ch. 75m. |  |  | GDP-II/MNK/Shib/W(B)-58 | 2 | bridge/culvert | 36606 | 0 | 54 | 366 | 2017-05-10 | M/S. Debesh Traders | 2016-03-10 | 2015-16 | GDP-II/MNK/Shib/W(B)-58 | 100 | 1 | 2016-03-20 |  | 100
317 |  |  | Construction of Housing for Landless & Privileged Muktijodha Project | CHLPMP | Construction of 03 nos.Cow shed & 03 nos.Poultry shed under CHLUMP for Muktijodha 1. Md. Abul Kachem 2. Shongkor Proshad Voumik & 3. Md. Monsur Ali at Shibalaya Upazila, Dist.: Manikganj.( Shibalaya Part) |  |  | Chlump/Manikganj/S-1/17-18 | 10 | others | 36606 | 0 | 0 | 366 | 2018-05-22 | M/S. Leion Enterprise | 2017-11-22 | 2017-18 | MANIKGANJ/SHIBALAYA/H-2/13-14 | 100 | 1 | 2017-11-29 |  | 100
317 |  |  | Construction of Housing for Landless & Privileged Muktijodha Project | CHLPMP | (A) Construction of Housing for Sangkor Proshad Bhoumik village:Arua,Po: Maluchi (B) Construction of Housing for Md. Abul Kashem,Village: Dorikoyera,Po: Nali & (C) Construction of Housing for Md. Munsur Ali, Village: Laxmipur,Po: D.Tarail under Shibalaya Upazila, Dist.: Manikganj. |  |  | MANIKGANJ/SHIBALAYA/H-2/13-14 | 10 | others | 36606 | 0 | 0 | 366 | 2014-09-26 | M/S. Ema Construction | 2014-02-26 | 2014-15 | MANIKGANJ/SHIBALAYA/H-2/13-14 | 100 | 1 | 2014-03-05 |  | 100
100 |  |  | UCCP | UCCP | Construction of Mohadebpur Union Complex Bhaban under Shibalaya Upazila,District: Manikganj. |  |  | UCCP-2/MNK/SHI/2015-2016W | 10 | others | 36606 | 0 | 0 | 366 | 2017-05-08 | Starlite Services Ltd. | 2016-03-23 | 2016-17 | UCCP-2/MNK/SHI/2015-2016W | 100 | 1 | 2016-04-04 |  | 100
100 |  |  | UCCP | UCCP | Construction of Uthali Union Complex Bhaban under Shibalaya Upazila,District: Manikganj. |  |  | egp.Shib/Man/2017-18/Uthali UP/W-634 | 10 | others | 36606 | 0 | 0 | 366 | 2019-06-03 | M/S. Hanif Traders | 2018-08-29 | 2017-18 | egp.Shib/Man/2017-18/Uthali UP/W-634 | 20 | 0 | 2018-09-04 |  | 0
100 |  |  | UCCP | UCCP | Maintenance & Repair of Arua Union Complex Bhaban under Shibalaya Upazila,District: Manikganj. |  |  | e-Tender/LGED/Mank/Shib/UP-union/2016-17/W-01 | 10 | others | 36606 | 0 | 0 | 366 | 2017-08-28 | M/S. Debesh Traders | 2017-06-13 | 2017-18 | e-Tender/LGED/Mank/Shib/UP-union/2016-17/W-01 | 100 | 1 | 2017-06-30 |  | 100
409 |  |  | TULO | TULO | Construction of Mohadebpur & Ulail Land Office under Shibalaya Upazila,District: Manikganj. |  |  | TULO/MAN/W-02 | 10 | others | 36606 | 0 | 0 | 366 | 2018-09-30 | M/S. M.A Quddus | 2017-11-01 | 2017-18 | TULO/MAN/W-02 | 75 | 0 | 2017-12-03 |  | 60
95 |  |  | Particpatory Small Scale Water Resources Sector Project(PSSWRSP) | PSSWRSP | Construction of 5 Nos Lined Canal at Ch: 72m to 115m (Part-1), 383m to 733m (Part-2), 00m to 300m (Part-3), 330m to 630m (Part-4) and 100m to 266m (Part-5) under Kashadha CAD Subproject(SP-23108) under Shibalaya Upazila,District: Manikganj. |  |  | LGED/PSSW/PD/Shibalaya/Manikganj/01/2015 | 7 | rural waterways and ghats | 36606 | 0 | 0 | 366 | 42602 | JV. M/S. Mobarok Hossain & M/S. Ma Moni & Sons | 42236 | 2015-16 | LGED/PSSW/PD/Shibalaya/Manikganj/01/2015 | 100 | 1 | 42246 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Dhaka- Aricha NHW ( Aricha ghat- Paturia ghat Daskandi GPS)-Nali GC Road at Ch: 00-3315m & 3520-3567m . |  |  | e-Tender/LGED/Mank/ GOBM/17-18/W-12 | 1 | road | 36606 | 356782009 | 3362 | 366 | 2018-02-21 | M/S. Infinity Engineering Ltd. | 2017-12-18 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W-12 | 100 | 1 | 2017-12-24 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Uthali hat (Tara Mosque)-Jamduara via Belta Road at Ch: 62m-2130m. |  |  | e-Tender/LGED/Mank/GOBM/17-18/W-11 | 1 | road | 36606 | 356784040 | 2068 | 366 | 2018-02-21 | M/S. Infinity Engineering Ltd. | 2017-12-18 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W-11 | 100 | 1 | 2017-12-24 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Somesghor-Radhakantopur via Tobakhali Road at Ch: 00m-960m. |  |  | e-Tender/LGED/Mank/GOBM/17-18/W-02 | 1 | road | 36606 | 356784008 | 960 | 366 | 2018-02-08 | M/S. Chander Hat | 2017-12-05 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W-02 | 100 | 1 | 2017-12-11 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Dhusar bus Staand (Bazar)-Ghior GC via Nayabari Bazar Bardamankandi GPS Road at Ch: 00m-575m. |  |  | e-Tender/LGED/Mank/ GOBM/17-18/W-03 | 1 | road | 36606 | 356784001 | 575 | 366 | 2018-02-22 | M/S. Israfil Traders | 2017-12-17 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W-03 | 100 | 1 | 2017-12-24 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Uthali-Jaforgonj GC Road at Ch: 6800m-7365m & 7635-9150m. |  |  | e-Tender/LGED/Mank/ GOBM/17-18/W- | 1 | road | 36606 | 356782002 | 2118 | 366 | 2018-02-25 | M/S. Apex Enterprise | 2017-12-21 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W- | 100 | 1 | 2017-12-27 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Maintenance of Uthali-Nali GC Road at Ch: 5125m-7315m |  |  | e-Tender/LGED/Mank/ GOBM/17-18/W-39 | 1 | road | 36606 | 356782002 | 2190 | 366 | 2018-07-08 | M/S. Lamia Enterprise | 2018-04-25 | 2017-18 | e-Tender/LGED/Mank/ GOBM/17-18/W-39 | 100 | 1 | 2018-05-01 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Mintennce of Uthali-Nali GC road at Ch.00.00 m-2505 m. |  |  | e-Tender/LGED/Mank/ GOBM/18-19/W-27 | 1 | road | 36606 | 356782002 | 2505 | 366 | 2019-02-18 | M/S. Bashar Enterprise | 2018-11-18 | 2018-19 | e-Tender/LGED/Mank/ GOBM/18-19/W-27 | 100 | 1 | 2018-11-24 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Mintennce of Nayarchar - Nihonda ( Abdul Gani Sarker High School ) - Khanbari R&H Dakbanloo - Kalibari connecting Road. from Ch: 0.00-1500m |  |  | e-Tender/LGED/Mank/ GOBM/18-19/W-16 | 1 | road | 36606 | 356782006 | 1500 | 366 | 2019-01-22 | M/S. Reba Construction | 2018-11-22 | 2018-19 | e-Tender/LGED/Mank/ GOBM/18-19/W-16 | 100 | 1 | 2018-11-28 |  | 100
403 |  |  | Maintenance | GOBM | Periodic Mintennce of Shimulia UP Office (Darbar Sarif More)-Diarchar Sakrail bazar Road. At Ch: 500m-1664m |  |  | e-Tender/LGED/Mank/ GOBM/18-19/W-12 | 1 | road | 36606 | 356783004 | 1164 | 366 | 2019-01-19 | M/S. Village Enterprise | 2018-11-20 | 2018-19 | e-Tender/LGED/Mank/ GOBM/18-19/W-12 | 100 | 1 | 2018-11-26 |  | 100
345 |  |  | GSIDP | GSIDP | Improvement of east Baulikandha Sarbojonin Kalimondir under Arua union Latiude 23.558321 Longitude 89.653221 under Ahibalaya , Manikganj. |  |  | GSIDP/MNK/DW-10 | 10 | others | 36606 | 0 | 0 | 366 | 2018-11-11 | M/S. Meghna Builders | 2018-06-12 | 2018-19 | GSIDP/MNK/DW- | 100 | 1 | 2018-06-22
345 |  |  | GSIDP | GSIDP | Improvement of Shibalaya Centeral Soshan Ghat under Shibalaya union Latiude 23.840258 Longitude 89.799977 under Ahibalaya, Manikganj. |  |  | GSIDP/MNK/DW-08 | 10 | others | 36606 | 0 | 0 | 366 | 2018-11-11 | M/S. Meghna Builders | 2018-06-12 | 2018-19 | GSIDP/MNK/DW-08 | 0 | 0 | 2018-06-22
345 |  |  | GSIDP | GSIDP | Improvement of Jhoriarbag graveyard union Shibalaya Latitude 23.808367 Longitude 89.791533 under Shibalaya Upazila |  |  | GSIDP/MNK/DW-09 | 10 | others | 36606 | 0 | 0 | 366 | 2018-10-28 | M/S. Tanvir Enterprise | 2018-05-28 | 2018-19 | GSIDP/MNK/DW-09 | 100 | 1 | 2018-06-06
345 |  |  | GSIDP | GSIDP | Improvement of Radhakantopur Surbojanin Durga Mondir union Uthali Latitude 23.8630 Longitude 89.7936 under Shibalaya Upazila |  |  | GSIDP/MNK/DW-11 | 10 | others | 36606 | 0 | 0 | 366 | 2018-12-28 | M/S. Tanvir Enterprise | 2018-09-29 | 2018-19 | GSIDP/MNK/DW-11 | 100 | 1 | 2018-10-06
345 |  |  | GSIDP | GSIDP | Improvement of Kasobpatty Jame Mosque union Mohadebpur Latitude 23.8448 Longitude 89.8473 under Shibalaya Upazila |  |  | GSIDP/MNK/DW-12 | 10 | others | 36606 | 0 | 0 | 366 | 2019-01-05 | M/S. Simanta Enterprise | 2018-09-05 | 2018-19 | GSIDP/MNK/DW-12 | 0 | 0 | 2018-09-13